## Parameters
Complexity | LookupField | Complexity | Phase | Distribution Type | Distribution
Minor | Minor - Requirement Analysis | Minor | Requirement Analysis | Derived | 5%
Medium | Minor - Solution Outline & Design | Minor | Solution Outline & Design | Derived | 10%
Major | Minor - Testing | Minor | Testing | Derived | 10%
| Minor - Review & Rework | Minor | Review & Rework | Derived | 10%
| Minor - Documentation | Minor | Documentation | Derived | 5%
| Minor - Engineering Practices | Minor | Engineering Practices | Derived | 10%
| Minor - Deployment | Minor | Deployment | Fixed | 3
| Minor - Post Implementation Support | Minor | Post Implementation Support | Derived | 10%
| Minor - Contingency | Minor | Contingency | Derived | 10%
| Medium - Requirement Analysis | Medium | Requirement Analysis | Derived | 10%
| Medium - Solution Outline & Design | Medium | Solution Outline & Design | Derived | 15%
| Medium - Testing | Medium | Testing | Derived | 10%
| Medium - Review & Rework | Medium | Review & Rework | Derived | 20%
| Medium - Engineering Practices | Medium | Engineering Practices | Derived | 10%
| Medium - Deployment | Medium | Deployment | Fixed | 3
| Medium - Post Implementation Support | Medium | Post Implementation Support | Derived | 10%
| Medium - Contingency | Medium | Contingency | Derived | 10%
| Major - Requirement Analysis | Major | Requirement Analysis | Derived | 15%
| Major - Solution Outline & Design | Major | Solution Outline & Design | Derived | 20%
| Major - Testing | Major | Testing | Derived | 20%
| Major - Review & Rework | Major | Review & Rework | Derived | 20%
| Major - Engineering Practices | Major | Engineering Practices | Derived | 10%
| Major - Deployment | Major | Deployment | Fixed | 5
| Major - Post Implementation Support | Major | Post Implementation Support | Derived | 20%
| Major - Contingency | Major | Contingency | Derived | 10%

## Estimation
CR Complexity | Medium |  |  |  | Solution Architect |  | Technical Architect |  | RTE |  | Scrum Master |  | Product Manager |  | Product Owner |  | Technical Lead |  | Data Engineer |  | Platform Engineer
Phase | Ideal Distribution | Actual Distribution | Efforts | Activities Involved | Alloc (%) | Efforts | Alloc (%) | Efforts | Alloc (%) | Efforts | Alloc (%) | Efforts | Alloc (%) | Efforts | Alloc (%) | Efforts | Alloc (%) | Efforts | Alloc (%) | Efforts | Alloc (%) | Efforts
Requirement Analysis | 10% | 10% | 2 | CR Analysis, business meetings, data analysis
Solution Outline & Design | 15% | 15% | 0 | solution definition, logical and physical design, architecture
Development | Base | Base | 2.5 | Development, unit testing
Testing | 10% | 10% | 1 | Manual testing, test plan, test data creation, test results documentation
Review & Rework | 20% | 20% | 0.5 | Code review, comments, rework, final review.
Documentation | 10% | 10% | 0.25 | Documentation for all phases
Engineering Practices | 10% | 10% | 0.25 | Code quality
Deployment | Fixed | Fixed | 1 | RTL Process & Approvals
Post Implementation Support | 10% | 10% | 1 | Bug fixes, promotes, re-testing
Total |  |  | 6.5 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Contingency | 10% | 10% | 1
Total (Including Contingency) |  |  | 7.5 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Future ToDo:
1) % Allocation by Role and effort derivation
2) Calculate cost
3) Derive Schedule by PI / Sprint

## Sheet1
Changes are:
=> Analyse all the module that uses aircomm tables.
changes on Tables structure.
-> Parsing logic need to rework.
How many Sources: 15
How many Targets: 15
\
Complexity: medium ( parsing )
Dependency:
Risk